## Stakeholder Register Worksheet
Stakeholder Register Format
Name/Position | Organization | Role | R | A | C | I | Comments
Name / Position | Organization | Role | R | A | C | I | Comments
Marcus Wilson – Head of HR | Innovations Inc. | Project Sponsor |  | ✔ |  |  | Approves charter, funding, and major decisions; 2 hrs/week
Gloria Fisher – Project Manager | Innovations Inc. | Project Manager | ✔ |  |  |  | Manages planning, execution, coordination; 20 hrs/week
Hiroshi Tanaka – IT Lead | Innovations Inc. (IT) | IT Support Lead | ✔ |  |  |  | AV, conference room tech, equipment setup; 20 hrs
Ursula Miller – Finance Lead | Innovations Inc. (Finance) | Financial Oversight |  |  | ✔ |  | Funding, cost tracking, allocations; 2 hrs
Priya Sanders – Marketing Lead | Innovations Inc. (Marketing) | Marketing Materials | ✔ |  |  |  | Manuals, brochures, gift packs; 25 hrs
Sam Manning – Facilities Lead | Innovations Inc. (Facilities) | Campus Tours | ✔ |  |  |  | Plans and schedules campus tours; 10 hrs
Marvin Coleman – Catering Manager | Innovations Inc. | Catering Coordination | ✔ |  |  |  | Manages Happy Catering contract
Sunny Marsh – Benefits Manager | Innovations Inc. (HR) | Benefits SME |  |  | ✔ |  | Benefits presentation; 3 hrs
Ram Finland – Continuing Education Lead | Innovations Inc. (HR) | Training SME |  |  | ✔ |  | Continuing education presentation; 3 hrs
Margaret Harrison – CEO | Innovations Inc. | Executive Stakeholder |  |  |  | ✔ | Executive visibility and updates; time not tracked
RACI Terms Defined | ROLE | DEFINED |  |  |  | Version:
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a Subject Matter Expert (SME)
| I | Inform as project progresses